## Sheet1
Continuous Improvement Plan for Exposure Assessment Strategies and Improving Exposure Judgments
Version 1.3 - Draft
2025-01-15
Gap | Five Year Goal (YE 2029) | Entitlement | Actions | By | Metric | From | To | Percent Complete | 2025 |  |  |  | Comments
[9 empty] | Q1 | Q2 | Q3 | Q4
The gaps identified in the survey that AIHA is seeking to improve. | The survey result you would hope to see if the survey were repeated at the end of 2029 | What you believe is a reasonable attainable ultimate survey result | What will be delivered at the end of the year. Brief description of how this connects to a multi-year effort. | The group or individual that has responsibility for completing the action. | What will be tracked and what the goal is for the end of the year. | Metric at Start of Year | Metric at End of Year | Metric at Progress Interval | Red-Yellow-Green Status by Quarter
Initiative I. Increase AIHA Exposure Assessment Strategy Training and Awareness
Only 35% of technical leaders have received training on the Exposure Assessment Strategy. (Q10) Twenty-two percent (22%) of all respondents to the SOTAvP survey on Occupational Exposure Assessment indicated that they were not familiar with the AIHA Strategy . Twenty-one percent of respondents indicated that lack of training was a barrier to exposure assessment. (Q39) | 75% of technical leaders will have training on EAS <10% of respondents will be unfamiliar with the AIHA Strategy <10% of respondents will cite lack of training as a barrier to exposure assessment. | 95% of technical leaders will have training on EAS <5% of respondents will be unfamiliar with the AIHA Strategy <5% of respondents will cite lack of training as a barrier to exposure assessment. | Develop new Academic Faculty slide decks (with WIIFMa messaging and applicable to US & global audiences). | AIHA Staff - (CEO/CSO), EASC & IEJ-AG | Create slide deck in Q1 | 0 | 1
|  |  | Develop new student focused slide decks (with WIIFM messaging and applicable to US & global audiences). |  | Create slide deck Q1 | 0 | 1
|  |  | Refine slide deck aimed at practitioners currently used for local sections |  | Refine slide deck Q1 | 0 | 1
|  |  | Develop a pool of curated guest lecturers (separate from the Distinguished Lectures) |  | Develop pool of guest lecturers in Q1 | 0 | 1
|  |  | Conduct Outreach to Academic Training programs to raise awareness and engagement |  | Present to 5 academic training programs by YE25 | 0 | 5
|  |  | Conduct Outreach to student local sections to raise awareness and engagement |  | Present to 5 student local sections by YE25 | 0 | 5
|  |  | Conduct Outreach during Leadership Training |  | Present at Leadership Workshop | 0 | 1
|  |  | Conduct Outreach to local setions to raise awareness and engagement |  | Present to 15 local sections by YE25 | 0 | 15
Initiative II. Develop and Deliver Key Messaging at 2025 AIHA Connect: Why Need to Change and Implement the AIHA Exposure Assessment Strategy
About 1/5 (19%) respondents closely follow the AIHA Strategy for Assessment and Managing Occupational Exposures and approximately 1/5 (17%) are not familiar with the strategy. The remainder (64%) indicate that they are familiar with and/or somewhat follow the strategy. | 40% closely follow the strategy | 95% closely follow the strategy | Draft key messaging for ALL practitioners --- Why practices need to change and what needs to be done. Delivery channels at AIHA Connect include Main Stage, Session presentations, Q&A Sessions, Handouts) and can be amplified via Catalyst, Synergist, social media platforms pre-and post-event. | AIHA Staff - (CEO, CXO and CSO), John Mulhausen | Draft Messaging in Q1 | 0 | 100%
[5 empty] | AIHA Connect 2025 Q2 | 0 | 100%
Initiative III. Develop Key Messaging and Resources That Practitioners Can Use to Influence Employers and Clients
Thirty-four percent (34%) of respondents say that lack of support is a barrier to exposure assessment. (38% if corporate and 30% if consultants) Thirty-three percent (33%) said that inability to demonstrate the business case is a barrier. | 15% of respondents say that lack of support and ability to make the business case is a barrier to exposure assessment. | 5% of respondents say that lack of support ability to make the business case is a barrier to exposure assessment. | Develop key messaging and resources for practitioners to help them influence employers and/or clients. - What to influence - How to influence: Framing and Selling the Need for Change. Compelling Language and Techniques Proven Successful | AIHA Staff - (CEO, CSO, Marketing Director), EASC, IEJ-AG | Develop by YE 2025 | 0 | 100% | [5 empty] | Notes:
a. Leverage fact that operations personnel are conversant in statistical ideas.
b. Emphasize importance of transparency regarding uncertainty
c. Communicate availability of resources to help people get started are available. (e.g., PGP, Model Programs, EA Tools)
d. Reinforce this is a continuous improvement journey.
Initiative IV. Develop Self-Assessment Tools
Only 36% of exposure assesment technical leaders have specific training in statistical analysis. Only 34% say that the lack of training on Bayesian statistical tools is a barrier to exposure assessment. | <15% of respondents cite lack of training as a barrier to exposure assessment. | <5% of respondents will cite lack of training as a barrier to exposure assessment. | Create and deploy a Self Assessment Tool - Use PGP structure as organizing tool to figure point of entry into the EAS. Embellish existing content to develop self assessment. | AIHA Staff - CSO, CLO, EASC | Develop by Q3 2025 | 0 | 100%
|  |  |  | EASC, IEJ-AG to leverage Local Sections, VPP Conferences, Management Systems Compliance | Present to 3 active local sections by YE 2025 | 0 | 10 | [5 empty] | Present to 30 active local sections by YE 2026
Initiative V. Require That AIHA Connect Presenters Use Appropriate Statistical Analysis
Twenty-two percent (22%) of all respondents to the SOTAvP survey on Occupational Exposure Assessment indicated that they were not familiar with the AIHA Strategy . | <10% of respondents will be unfamiliar with the AIHA Strategy | <5% of respondents will be unfamiliar with the AIHA Strategy | Require educational content presenters to use statistical analysis in AIHA Connect presentations as part of the approval process for proposals. | AIHA Staff - CSO, CLO, CXO | AIHA Connect 2026 Planning / Call for Abstracts Q3 2025 | 0 | 1
Initiative VI. Create and Deploy Support Groups for Users of Statistics and Modeling Tools
Twenty-one percent of respondents indicated that lack of training was a barrier to exposure assessment. (Q39) | <15% of respondents will cite lack of training as a barrier to exposure assessment. | <5% of respondents will cite lack of training as a barrier to exposure assessment. | Provide support via user's groups (Catalyst), FAQs, Apple Wizards, Resource Guide | AIHA Staff - CSO, EASC, IEJ-AG | Set up Catalyst Group, FAQs in Q1, Resource Guide Q2, Explore options for other resources Q3 | 0 | 3
Continuously Improve This Plan
New Gaps Identified by latest SOTAvP Survey | Significant reduction in key gaps identified by the latest survey | Near-complete elimination of key gaps identified by the latest survey | ID Key Gaps identified by latest survey | AIHA CSO, Key VGs (typically the VGs involved in the PGPs explored in the Survey) | Key Gaps identified by Q3 of year following the survey
|  |  | Planning Session to revise CIP in light of newly identified Key Gaps | Key AIHA Staff, Key AIHA BOD, Key VG Representatives | Planning session complete by Q3 or Q4 of year following the Survey
|  |  | Revised plan approved by AIHA BOD | AIHA BOD | BOD approved by Q4 of year following the Survey
aWhat's In It For Me?
2023-AIHA-Airborne-Chemical-Exposure-Assessment-Survey-Final-Report.pdf
Continuous Improvement Plan Brainstorming Session 20241007
Acknowledgments
John Mulhausen - Facilitator | Board of Directors | AIHA Staff
Lily Li | Nancy McClelland | Larry Sloan, CEO
Kimberley O'Connell | Bryan Seal | Bethany Chirico, CXO
Andy Becker | John Moore | Alla Orlova, CLO
Shannon Gaffney |  | Michele Twilley, CSO
Mark Stenzel |  | Angela Oler, Executive Director Registry Programs
Barry Graffeo |  | Jessie Lewis, Director Marketing
Roy Byer
Denis Logie
Michael Jayjock
Volunteer Matrix | IEJ
Training and Outreach | Pagone
Stenzel
AIHA Connect | Mulhausen
Influencers
Graffeo (limited to PI)
M. Johnson?
Users Group | Stenzel
Battista
Candee

## Sheet2
Continuous Improvement Plan for Exposure Assessment Strategies and Improving Exposure Judgments
Version 1.4
2025-04-23
Initiative I. Increase AIHA Exposure Assessment Strategy Training and Awareness
Gap | Five Year Goal | Entitlement | Actions | By | Metric | From | To | Percent Complete | 2025 |  |  |  | Comments
[9 empty] | Q1 | Q2 | Q3 | Q4
The gaps identified in the survey that AIHA is seeking to improve. | The survey result you would hope to see if the survey were repeated at the end of 2029 | What you believe is a reasonable attainable ultimate survey result | What will be delivered at the end of the year. Brief description of how this connects to a multi-year effort. | The group or individual that has responsibility for completing the action. | What will be tracked and what the goal is for the end of the year. | Metric at Start of Year | Metric at End of Year | Metric at Progress Interval | Red-Yellow-Green Status by Quarter
Only 35% of technical leaders have received training on the Exposure Assessment Strategy. (Q10) Twenty-two percent (22%) of all respondents to the SOTAvP survey on Occupational Exposure Assessment indicated that they were not familiar with the AIHA Strategy . Twenty-one percent of respondents indicated that lack of training was a barrier to exposure assessment. (Q39) | 75% of technical leaders will have training on EAS <10% of respondents will be unfamiliar with the AIHA Strategy <10% of respondents will cite lack of training as a barrier to exposure assessment. | 95% of technical leaders will have training on EAS <5% of respondents will be unfamiliar with the AIHA Strategy <5% of respondents will cite lack of training as a barrier to exposure assessment. | Develop new Academic Faculty slide decks (with WIIFMa messaging and applicable to US & global audiences). | AIHA Staff - (CEO/CSO), EASC & IEJ-AG | Create slide deck in Q1 | 0 | 1 | 100% |  |  |  |  | Working groups formed in Q1. Development of content was delayed but completed.
|  |  | Develop new student focused slide decks (with WIIFM messaging and applicable to US & global audiences). |  | Create slide deck Q1 | 0 | 1 | 100% |  |  |  |  | Working groups formed in Q1. Development of content was delayed but completed.
|  |  | Refine slide deck aimed at practitioners currently used for local sections |  | Refine slide deck Q1 | 0 | 1 | 100% |  |  |  |  | Working groups formed in Q1. Development of content was delayed but completed.
|  |  | Develop a pool of curated guest lecturers (separate from the Distinguished Lectures) |  | Develop pool of guest lecturers in Q1 | 0 | 1 | 100% |  |  |  |  | Working groups formed in Q1. Development of content was delayed but completed.
|  |  | Conduct Outreach to Academic Training programs to raise awareness and engagement |  | Present to 5 academic training programs by YE25 | 0 | 5 | 40% |  |  |  |  | Barrier identified through the process that academics feel that teaching biostatistics is sufficient to address the needs of the OEHS practitioner.
|  |  | Conduct Outreach to student local sections to raise awareness and engagement |  | Present to 5 student local sections by YE25 | 0 | 5 | 40% |  |  |  |  | 1 scheduled and 5 TBD for 2026
|  |  | Conduct Outreach during Leadership Training |  | Present at Leadership Workshop | 0 | 1 | 100%
|  |  | Conduct Outreach to local setions to raise awareness and engagement |  | Present to 15 local sections by YE25 | 0 | 15 | 47% |  |  |  |  | 7 TBD for 2026
Initiative II. Develop and Deliver Key Messaging at 2025 AIHA Connect: Why Need to Change and Implement the AIHA Exposure Assessment Strategy
About 1/5 (19%) respondents closely follow the AIHA Strategy for Assessment and Managing Occupational Exposures and approximately 1/5 (17%) are not familiar with the strategy. The remainder (64%) indicate that they are familiar with and/or somewhat follow the strategy. | 40% closely follow the strategy | 95% closely follow the strategy | Draft key messaging for ALL practitioners --- Why practices need to change and what needs to be done. Delivery channels at AIHA Connect include Main Stage, Session presentations, Q&A Sessions, Handouts) and can be amplified via Catalyst, Synergist, social media platforms pre-and post-event. | AIHA Staff - (CEO, CXO and CSO), John Mulhausen | Draft Messaging in Q1 | 0% | 100% | 100%
[5 empty] | AIHA Connect 2025 Q2 | 0 | 100% | 100%
Initiative III. Develop Key Messaging and Resources That Practitioners Can Use to Influence Employers and Clients
Thirty-four percent (34%) of respondents say that lack of support is a barrier to exposure assessment. (38% if corporate and 30% if consultants) Thirty-three percent (33%) said that inability to demonstrate the business case is a barrier. | 15% of respondents say that lack of support and ability to make the business case is a barrier to exposure assessment. | 5% of respondents say that lack of support ability to make the business case is a barrier to exposure assessment. | Develop key messaging and resources for practitioners to help them influence employers and/or clients. - What to influence - How to influence: Framing and Selling the Need for Change. Compelling Language and Techniques Proven Successful | AIHA Staff - (CEO, CSO, Marketing Director), EASC, IEJ-AG | Develop by YE 2025 | 0% | 100% | 100% |  |  |  |  | Notes:
a. Leverage fact that operations personnel are conversant in statistical ideas.
b. Emphasize importance of transparency regarding uncertainty
c. Communicate availability of resources to help people get started are available. (e.g., PGP, Model Programs, EA Tools)
d. Reinforce this is a continuous improvement journey.
Initiative IV. Develop Self-Assessment Tools
Only 36% of exposure assesment technical leaders have specific training in statistical analysis. Only 34% say that the lack of training on Bayesian statistical tools is a barrier to exposure assessment. | <15% of respondents cite lack of training as a barrier to exposure assessment. | <5% of respondents will cite lack of training as a barrier to exposure assessment. | Create and deploy a Self Assessment Tool - Use PGP structure as organizing tool to figure point of entry into the EAS. Embellish existing content to develop self assessment. | AIHA Staff - CSO, CLO, EASC | Develop by Q3 2025 | 0 | 100% | 95% |  |  |  |  | EASC volunteers have created content and PointerPro software is used to host the Self Assessment Tool.
|  |  |  | EASC, IEJ-AG to leverage Local Sections, VPP Conferences, Management Systems Compliance | Present to 3 active local sections by YE 2025 | 0 | 30 | 0% |  |  |  |  | Present to 30 active local sections by YE 2026
Initiative V. Require That AIHA Connect Presenters Use Appropriate Statistical Analysis
Twenty-two percent (22%) of all respondents to the SOTAvP survey on Occupational Exposure Assessment indicated that they were not familiar with the AIHA Strategy . | <10% of respondents will be unfamiliar with the AIHA Strategy | <5% of respondents will be unfamiliar with the AIHA Strategy | Require educational content presenters to use statistical analysis in AIHA Connect presentations as part of the approval process for proposals. | AIHA Staff - CSO, CLO, CXO | AIHA Connect 2026 Planning / Call for Abstracts Q3 2025 | 0 | 1 | 100% |  |  |  |  | TASK COMPLETE: 2026 conference proposal responses will inform decisions for 2027
Initiative VI. Create and Deploy Support Groups for Users of Statistics and Modeling Tools
Twenty-one percent of respondents indicated that lack of training was a barrier to exposure assessment. (Q39) | <15% of respondents will cite lack of training as a barrier to exposure assessment. | <5% of respondents will cite lack of training as a barrier to exposure assessment. | Provide support via user's groups (Catalyst), FAQs, Apple Wizards, Resource Guide | AIHA Staff - CSO, EASC, IEJ-AG | Set up Catalyst Group, FAQs in Q1, Resource Guide Q2, Explore options for other resources Q3 | 0 | 3 | 100% |  |  |  |  | Task groups formed in Q1 and roster used to establish Catalyst group and populate page with resources.
Continuously Improve This Plan
New Gaps Identified by latest SOTAvP Survey | Significant reduction in key gaps identified by the latest survey | Near-complete elimination of key gaps identified by the latest survey | ID Key Gaps identified by latest survey | AIHA CSO, Key VGs (typically the VGs involved in the PGPs explored in the Survey) | Key Gaps identified by Q3 of year following the survey | 0 | 100% | 100%
|  |  | Planning Session to revise CIP in light of newly identified Key Gaps | Key AIHA Staff, Key AIHA BOD, Key VG Representatives | Planning session complete by Q3 or Q4 of year following the Survey | 0 | 100% | 90% |  |  |  |  | Meetings will be held in Q1 of 2026
|  |  | Revised plan approved by AIHA BOD | AIHA BOD | BOD approved by Q4 of year following the Survey | 0 | 100% | 80% |  |  |  |  | Board approval expected in Q1 2026
aWhat's In It For Me?
2023-AIHA-Airborne-Chemical-Exposure-Assessment-Survey-Final-Report.pdf
Continuous Improvement Plan Brainstorming Session 20241007
Acknowledgments
John Mulhausen - Facilitator | Board of Directors | AIHA Staff
Lily Li | Nancy McClelland | Larry Sloan, CEO
Kimberley O'Connell | Bryan Seal | Bethany Chirico, CXO
Andy Becker | John Moore | Alla Orlova, CLO
Shannon Gaffney |  | Michele Twilley, CSO
Mark Stenzel |  | Angela Oler, Executive Director Registry Programs
Barry Graffeo |  | Jessie Lewis, Director Marketing
Roy Byer
Denis Logie
Michael Jayjock
Volunteer Matrix | IEJ
Training and Outreach | Pagone
Stenzel
AIHA Connect | Mulhausen
Influencers
Graffeo (limited to PI)
M. Johnson?
Users Group | Stenzel
Battista
Candee

## brief
Continuous Improvement Plan
2025 Initiatives - Exposure Assessment | Status | Key:
I. Increase AIHA Exposure Assessment Strategy Training and Awareness |  | On Track
II. Develop and Deliver Key Messaging at 2025 AIHA Connect: Why Need to Change and Implement the AIHA Exposure Assessment Strategy |  | Behind
III. Develop Key Messaging and Resources That Practitioners Can Use to Influence Employers and Clients |  | At Risk
IV. Develop Self-Assessment Tools |  | Not Started
V. Explore how AIHA Connect Presenters Use Appropriate Statistical Analysis
VI. Create and Deploy Support Groups for Users of Statistics and Modeling Tools
Continuously Improve This Plan